## Slide 1: Chapter 5
SOFTWARE PROJECT PLANNING

## Slide 2
PROJECT PLANNING OBJECTIVES
The objective of software project planning is to provide a framework that enables the manager to make reasonable estimates of resources, cost, and schedule. These estimates are made within a limited time frame at the beginning of a software project and should be updated regularly as the project progresses.
SOFTWARE SCOPE
The first activity in software project planning is the determination of software scope.
It means figuring out exactly what the software will do, how it will perform, and what it should not do.
It's like creating a clear picture of the software’s boundaries. It includes :-
Data and control: What kind of information the software will handle, and how it will manage that information.
Function: What tasks or actions the software will perform.
  Performance: How fast or efficient the software should be. For example, how long it should take to process a request or provide a response.
  Constraints: Limits or restrictions that are outside the software, like how much memory it can use or compatibility with other systems.
  Interfaces: How the software will communicate or connect with other systems or hardware.
  Reliability: How dependable the software needs to be, making sure it doesn't crash or have issues.

## Slide 3
Refining the Scope: Once the software's functions are described, they may need to be refined to add more details. The more clearly you define what needs to be done, the easier it will be to plan.
Decomposing the Work: When estimating how long the project will take or how much it will cost, breaking the work into smaller tasks is helpful. This makes it easier to get accurate estimates.
At the beginning of a software project, the problem and goals are broadly defined, but details about what the software needs to do (scope) are still unclear. Scope is prerequisite for estimation.
The most commonly used technique to bridge the communication gap between the customer and developer and to get the communication process started is to conduct a preliminary meeting or interview.
This first meeting is often uncomfortable, like a first date. Both sides might feel unsure about what to say or ask, fearing they’ll be misunderstood. Despite the awkwardness, both parties want the meeting to succeed and lead to a productive relationship.
Gause and Weinberg suggest that the analyst start by asking context-free questions; that is, a set of questions that will lead to a basic understanding of the problem.
Obtaining Information Necessary for Scope

## Slide 4
The first set of context-free questions focuses on the customer.
For example, the analyst might ask:
  • Who is behind the request for this work?
  • Who will use the solution?
  • What will be the economic benefit of a successful solution?
  • Is there another source for the solution?
The next set of questions enables the analyst to gain a better understanding of the problem :
  • How would you (the customer) characterize "good" output that would be generated by a successful solution?
  • What problem(s) will this solution address?
  • Can you show me (or describe) the environment in which the solution will be used?
  • Will any special performance issues or constraints affect the way the solution is approached?
The final set of questions focuses on the effectiveness of the meeting. Gause and Weinberg call these "meta-questions" :
  • Are you the right person to answer these questions? Are answers "official"?
  • Are my questions relevant to the problem that you have?
  • Am I asking too many questions?
  • Can anyone else provide additional information?
  • Should I be asking you anything else?

## Slide 5
These questions (and others) will help to "break the ice" and initiate the communication that is essential to establish the scope of the project. But a question and answer meeting format is not an approach that has been overwhelmingly successful. In fact, the Q&A session should be used for the first encounter only and then be replaced by a meeting format that combines elements of problem solving, negotiation, and specification.
FAST (facilitated application specification techniques):-
Following problem arises during the normal communication :-
Customers and software engineers often unconsciously view each other as separate groups rather than as a unified team working toward a common goal ."Us vs. Them" Mentality.
Instead of collaborating, each side tends to stay in its own "territory" and relies on formal methods like memos, position papers, and Q&A sessions to communicate.
The lack of real collaboration leads to confusion and misinterpretation.
Without trust and cooperation, a strong working relationship doesn’t develop.

## Slide 6
With these problems in mind, a number of independent investigators have developed a team-oriented approach to requirements gathering that can be applied to help establish the scope of a project. Called facilitated application specification techniques (FAST).
This approach encourages the creation of a joint team of customers and developers who work together to identify the problem.
propose :-
elements of the solution,
negotiate different approaches,
specify a preliminary set of requirements.
Feasibility
Once scope has been identified it is reasonable to ask: “Can we build software to meet this scope? Is the project feasible?”
Teams frequently skip this step, often due to pressure from impatient managers or customers, which leads to projects failing later.
Software feasibility has four solid dimensions:
1.Technology— Is a project technically feasible? Can defects be reduced to a level matching the application’s needs?
2.Finance—Is it financially feasible? Can development be completed at a cost the software organization, its client, or the market can afford?
3.Time--Can the project be delivered on time, especially in competitive markets where time-to-market is critical?
4.Resources--Does the organization have the necessary team, tools, and infrastructure to execute the project?

## Slide 7
Putnam and Myers correctly suggest that scoping is not enough. Once scope is understood, the software team and others must work to determine if it can be done within the dimensions just noted. This is a crucial, although often overlooked, part of the estimation process.
A Scoping Example:-
Conveyor line sorting system (CLSS)
Communication with the customer leads to a definition of the data and control that are processed, the functions that must be implemented, the performance and constraints that bound the system, and related information. As an example, consider software for a conveyor line sorting system (CLSS).
The statement of scope for CLSS follows:
The conveyor line sorting system (CLSS) sorts boxes moving along a conveyor line. Each box is identified by a bar code that contains a part number and is sorted into one of six bins at the end of the line. The boxes pass by a sorting station that contains a bar code reader and a PC. The sorting station PC is connected to a shunting mechanism that sorts the boxes into the bins. Boxes pass in random order and are evenly spaced. The line is moving at five feet per minute

## Slide 8
The project planner examines the statement of scope and extracts all important software functions. This process, called decomposition. results in the following functions:
  • Read bar code input.
  • Read pulse tachometer.
  • Decode part code data.
  • Do database look-up.
  • Determine bin location.
  • Produce control signal for shunt.
  • Maintain record of box destinations.

## Slide 9
RESOURCES
The second software planning task is estimation of the resources required to accomplish the software development effort.
The development environment—hardware and software tools—sits at the foundation of the resources pyramid and provides the infrastructure to support the development effort.
At a higher level, we encounter reusable software components—software building blocks that can dramatically reduce development costs and accelerate delivery.
At the top of the pyramid is the primary resource—people.
Each resource is specified with four characteristics:
  description of the resource
  a statement of availability
  time when the resource will be required
  duration of time that resource will be applied.
The last two characteristics can be viewed as a time window.

## Slide 10
1.Human Resources
The project planner starts by understanding the scope of the project—what needs to be accomplished.
Based on the scope, the planner identifies the specific skills needed to complete the development tasks.
The planner determines both the organizational roles (e.g., manager, senior software engineer) and specializations (e.g., telecommunications, database, client/server systems) required for the project. For small projects (e.g., less than one person-year of effort), a single person might handle multiple roles and consult with specialists as needed.
The number of people required for the project depends on the total development effort estimated, often expressed in person-months (the amount of work one person can complete in a month).
2.Reusable Software Resources
The concept of reusable software resources focuses on Component-Based Software Engineering (CBSE), which aims to build and utilize software components that can be reused across projects. This approach increases efficiency, reduces cost, and improves quality by reusing existing resources.
Key Characteristics of Reusable Components:
  Cataloged: Components should be organized in a way that they are easy to locate when needed.
  Standardized: Components must follow consistent standards, making them compatible across different applications.
  Validated: Components should be thoroughly tested to ensure they integrate seamlessly into new systems.

## Slide 11
Four Software Resource Categories (as suggested by Bennatan):
Off-the-Shelf Components:
  Pre-existing, commercial components that can be directly used in the project.
  Examples: Third-party libraries, frameworks, or tools.
Full-Experience Components:
  Entire systems or subsystems previously developed and operational.
  They can be reused with minimal modifications.
Partial-Experience Components:
  Reusable fragments or smaller parts of software that require some adjustments or enhancement to fit the current project.
  Examples: Modules, classes, or functions.
New Components:
  Freshly developed components tailored specifically for the current project.
  These may eventually be cataloged and standardized for future reuse.
Environmental Resources
The environment that supports the software project, often called the software engineering environment (SEE), incorporates hardware and software. Hardware provides a platform that supports the tools (software) required to produce the work products that are an outcome of good software engineering practice.

## Slide 12
Software sizing is the process of estimating how big a software project is. It helps measure how much work is needed to complete the project. Think of it like figuring out the size of a task before starting it, so you can plan better, like estimating how much time, effort, or resources you'll need.
Software Sizing
Project estimate is only as good as the estimate of the size of the work to be accomplished, sizing represents the project planner’s first major challenge. In the context of project planning, size refers to a quantifiable outcome of the software project.
  If a direct approach is taken, size can be measured in LOC.
  If an indirect approach is chosen, size is represented as FP.
Putnam and Myers suggest four different approaches to the sizing problem:
1.Fuzzy Logic Sizing :-This method uses approximate reasoning to estimate the software size.
Steps:
Identify the type of application (e.g., a website, mobile app, or desktop software).
Assign a rough size (like small, medium, or large).
Refine the size further within the chosen range using your experience and a project database
Example:
If you're building an app, you might call it "medium-sized" and then adjust the estimate based on past projects.

## Slide 13
2.Function Point Sizing
This involves analyzing the features and functions of the software.
Steps:
  Measure things like how much data is handled, how many user interactions exist, and how complex the software is.
  Use predefined metrics to calculate the size.
Example: If a software has many data inputs and outputs, the size estimate will be larger.
3.Standard Component Sizing
Software is broken into standard building blocks or components like : Screens, reports, programs, files, and lines of code (LOC).
Steps:
  Count how many of each component the software will have.
  Use historical data to estimate the size for each type of component.
4.Change Sizing
This is used when you’re modifying existing software instead of building from scratch.
Steps:
Estimate the type and number of changes needed, such as:
  Reusing existing code.
  Adding new code.
  Changing or deleting code.
Use effort ratios (how much work each type of change typically takes) to calculate the size.

## Slide 14
Problem-Based Estimation is a method of estimating the effort, time, and cost of a software project by breaking it into smaller tasks or components. Each task is measured using metrics like Lines of Code (LOC) or Function Points (FP) to calculate how much work is needed. Historical data is used to improve accuracy. This technique uses measures like Lines of Code (LOC) or Function Points (FP) to estimate the size, effort, and cost of a software project.
Problem-Based Estimation
Start with a Scope Statement:
  Define what the software needs to do (its overall purpose).
Break the Project into Smaller Pieces:
  Divide the project into functions or components (e.g., login system, payment system).
Choose a Sizing Measure:
  Use LOC (how many lines of code it will take) or FP (how many user interactions, outputs, or data flows).
  For LOC: Focus on dividing functions into small tasks that match past projects.
  For FP: Focus on inputs, outputs, data files, and external interactions.
Use Baseline Metrics:
  Metrics from past projects (like "LOC per person-month" or "FP per person-month") are used to calculate the effort required for the project.
  Domain-specific metrics: Different types of projects (e.g., mobile apps, banking systems) have unique productivity rates. Use data that matches the kind of project you're estimating.

## Slide 15
Estimate a Range of Values:
For each function, provide three estimates:
  Optimistic (best-case): The minimum size or effort needed.
  Most likely: The realistic size or effort based on experience.
  Pessimistic (worst-case): The maximum size or effort needed.
Calculate the Expected Value (Weighted Average):
optimistic (Sopt), most likely (Sm), and pessimistic (Spess) estimates.
Use the formula: S = (Sopt + 4Sm + Spess)/6​​